## Register
INSTRUMENT INSTALLATION REGISTER
S.No | Tag No | Instrument | Loc | Mounted on | Tubing | Remarks
1 | PT-1104 | Pressure transmitter | A1 | 2026-09-01 | 9-Sep
2 | LT4011 | Level transmitter | A4 | 2026-09-01 | 2026-09-07
3 | FT-2035 | Flow transmitter | A3 | 2026-09-05 | pending
4 | TT-1105 | Temperature transmitter | A1 | 2026-09-07 | N/A
5 | FT 1101 | Flow transmitter | Area-1 | 2026-09-12 | 2026-09-16 | cal cert recd
6 | PT-1102 | Pressure transmitter | A1 | 12-Sep | pending
7 | PT2042 | Pressure transmitter | A3 | 16-Sep | pending | stand ok
8 | TT-4013 | Temperature transmitter | A4 | 16-Sep | N/A